## Stories
ID | Story | Size | Priority | Semir | LIli | Alex | Francis | Ayusha | Average | rank
1 | As a student, I want to search the system for a specific item, so I can see all the resources available to the related to the topic | 6 | 1 | 8 | 1 | 5 | 1 | 3 | 3.6 | 1
2 | As a student I want to see the list of items borrowed when I log in to the library system, so that I can see all the items I have borrowed | 3 | 13 | 12 | 12 | 6 | 14 | 6 | 10 | 13
3 | As a student I want to checkout the item so I that I can use it outside the library | 3 | 2 | 1 | 3 | 7 | 4 | 4 | 3.8 | 2
4 | As a librarian, I want the system to auto generate a holds report so that I’ll be able to hold the item until the client takes it | 5 | 6 | 4 | 8 | 4 | 3 | 8 | 5.4 | 6
5 | As a librarian, I want to list down customer requests for new titles which sends orders automatically to be able to update the current library for the patrons | 3 | 15 | 9 | 15 | 10 | 12 | 14 | 12 | 15
6 | As a student, I want to be able to reserve an item to put on hold to be able to take it home later on. | 4 | 5 | 5 | 2 | 3 | 2 | 13 | 5 | 5
7 | As a librarian, I want to be able to register clients in the system | 4 | 3 | 3 | 9 | 2 | 7 | 2 | 4.6 | 3
8 | As a librarian, I want to be able to remove membership status from clients in the system | 4 | 11 | 7 | 11 | 11 | 8 | 12 | 9.8 | 11
9 | As a student, I want to register as a client to be able to use the library services. | 4 | 14 | 13 | 14 | 15 | 6 | 11 | 11.8 | 14
10 | As a librarian, I want to be able to add new titles in the system so that the catalogue is up to date | 3 | 4 | 10 | 4 | 1 | 9 | 1 | 5 | 4
11 | As a librarian, I want to be able to delete titles in the system so that the catalogue is up to date | 3 | 8 | 11 | 5 | 9 | 10 | 6 | 8.2 | 8
12 | As a student, I want to check in an item, to be able to return it. | 3 | 7 | 2 | 7 | 4 | 11 | 5 | 5.8 | 7
13 | As a student, I want to be able to cancel my hold order | 3 | 9 | 6 | 6 | 14 | 5 | 10 | 8.2 | 9
14 | As a student I want to be able to extend borrow time frame for individual items | 4 | 10 | 14 | 10 | 13 | 13 | 9 | 11.8 | 10
15 | As a student, I want to be able to edit my profile just in case I might change my phone number or home address. | 5 | 12 | 2 | 13 | 12 | 15 | 7 | 9.8 | 12
As a librarian, I want to see the statistics of items.
As a student, I should be able to pay an item when it is overdue.
As a librarian I want to remove a client from the system.
ID | Story | Size | Priority
1 | As a student, I want to search the system for a specific item, so I can see all the resources available to the related to the topic | 6 | 1 | 1 | [5 empty] | 1
3 | As a student I want to checkout the item so I that I can use it outside the library | 3 | 2 | 2 | [5 empty] | 2
7 | As a librarian, I want to be able to register clients in the system | 4 | 3 | 3 | [5 empty] | 3
10 | As a librarian, I want to be able to add new titles in the system so that the catalogue is up to date | 3 | 4 | 4 | [5 empty] | 4
6 | As a student, I want to be able to reserve an item to put on hold to be able to take it home later on. | 4 | 5 | 5 | [5 empty] | 5
4 | As a librarian, I want the system to auto generate a holds report so that I’ll be able to hold the item until the client takes it | 5 | 6 | 6 | [5 empty] | 6
12 | As a student, I want to check in an item, to be able to return it. | 3 | 7 | 7 | [5 empty] | 7
11 | As a librarian, I want to be able to delete titles in the system so that the catalogue is up to date | 3 | 8 | 8 | [5 empty] | 8
13 | As a student, I want to be able to cancel my hold order | 3 | 9 | 9 | [5 empty] | 9
14 | As a student I want to be able to extend borrow time frame for individual items | 4 | 10 | 10 | [5 empty] | 10
8 | As a librarian, I want to be able to remove membership status from clients in the system | 4 | 11 | 11 | [5 empty] | 11
15 | As a student, I want to be able to edit my profile just in case I might change my phone number or home address. | 5 | 12 | 12 | [5 empty] | 12
2 | As a student I want to see the list of items borrowed when I log in to the library system, so that I can see all the items I have borrowed | 3 | 13 | 13 | [5 empty] | 13
9 | As a student, I want to register as a client to be able to use the library services. | 4 | 14 | 14 | [5 empty] | 14
5 | As a librarian, I want to list down customer requests for new titles which sends orders automatically to be able to update the current library for the patrons | 3 | 15 | 15 | [5 empty] | 15

## Tasks
| As a student, I want to search the system for a specific item, so I can see all the resources available to the related to the topic | Predecessor | Days | People | Employees
| Create new class Search that contains an overloaded method that retrieves library items description and availability based on any provided search criteria |  |  |  | Tester A
| Create database connectivity by writing an SQL string to connect and retrieve searched items from relevant tables in the database |  |  |  | Tester B
| Test search method by typing various search queries |  |  |  | Programmer A
| Fix bugs found during testing |  |  |  | Programmer B
| Create web pages for entering and returning search items and link these pages to the main library website |  |  |  | Programmer C
| Test search feature in main library website |  |  |  | Project Manager
DB Manager
Feature 2 | As a student I want to checkout the item so I that I can use it outside the library | Predecessor | Days | People
1 | Create checkout method that reads barcode numbers from library items |  | 2
2 | Create db? | 1 | 1
3 | Connect method to the database to record the scanned items with information on the library item and the borrower | 2 | 1
4 | Test checkout method by scanning random items | 3 | 2
5 | Fix bugs found during testing | 4 | 1
Integrate with current running software and test feature again by scanning more items
Feature 3 | As a librarian I want to be able to register clients into the system | Predecessor | Days
1 | Create a registration form |  | 1
2 | Create a Register method that submits the form | 1 | 2
3 | Create a database connectivity to client records | 2 | 1
4 | Test method by creating test user accounts | 3 | 1
5 | Fix bugs found during testing | 4 | 2
6 | Integrate from and method into system and test | 5 | 1
Feature 4 | As a librarian, I want to be able to add new titles in the system so that the catalogue is up to date | Predecessor | Days
1 | Create a form for registering new items |  | 1
2 | Create a method that takes the values inside the form and store to database | 1 | 2
3 | Create a connectivity to the database | 2 | 1
4 | Test the method if it stores new items succesfully | 3 | 1
5 | Fix bugs found during testing | 4 | 2
6 | Integrate the form and method inside the current build of system | 5 | 2
Feature 5 | As a student, I want to be able to reserve an item to put on hold to be able to take it home later on.
1 | Create a reserve method to put a hold on the book that the student wants to borrow |  | 2
2 | Connect method to the database to record item and borrower information | 1 | 1
3 | Test method with various users and items | 2 | 1
4 | fix bugs found during testing | 3 | 2
5 | Integrate method into software system and test | 4 | 2
Feature 6 | As a librarian, I want the system to auto generate a holds report so that I’ll be able to hold the item until the client takes it | Predecessor | Days
1 | Create a class for 'on hold' items that contains an overload method that retrieves 'on hold' items, documentation and notifies a librarian |  | 2
2 | Connect the method to the database | 1 | 1
3 | Test the method with user/librarian | 2 | 1
4 | Fix found bugs | 3 | 2
5 | Integrate the methods on the current system | 4 | 2
Feature 7 | As a student, I want to check in an item, to be able to return it. | Predecessor | Days
1 | Create a checkIn method which records the item as physically in the library and no longer in the care of borrower |  | 2
2 | Connect method to database to record item information and update status |  | 1
3 | Test method with tester items that were borrowed to ensure that status updates |  | 1
4 | fix any bugs found in the testing phase |  | 2
5 | integrate method into software system and conduct final testing |  | 2
START | Search Feature and Database prep
| Plan and Designing the Systems Database |  | 5 | DB Manager
| Create the designed Database |  | 2 | DB Manager
| Test and review the created Database |  | 2 | DB Manager, Project Manager
Feature 8 | As a librarian, I want to be able to delete titles in the system so that the catalogue is up to date
1 | Create method called deleteItems that shows existing items in database and option to delete selected items
2 | Test deleteItems method using test items
3 | Debug delelteItems method
4 | Implement deleteItems method into main system and test
Feature 9 | As a student I want to be able to view my hold order
1 | Create a viewHold method in which user can view all items on hold by that individual
2 | Test the viewHold method using test users and test items
3 | Debug viewHold method
4 | Implement viewHold method into main system and test
Feature 10 | As a student, I want to be able to cancel my hold order (DEPENDS ON FEATURE 9)
1 | Create method called cancelHold which cancels holds
2
3
4
Feature 11 | As a librarian, I want to be able to add new titles in the system so that the catalogue is up to date
1 | Create a form for adding new items
2 | Create an add method that adds new items to the database integrated with the form
3 | Connect add method to database and test connectivity
4 | Test the add method with the database connectivity
5 | Integrate the add method on the current system
Feature 12 | As a librarian, I want to be able to delete titles in the system so that the catalogue is up to date
1 | Create a view of datasets of the items in possession
2 | Create a delete method that works with the dataset view and deletes selected records
3 | Connect method to database
4 | Test the method if it works with the database
5 | Fix bugs if found
6 | Integrate the add method on the current system
Feature ?? | View items in database
Create method called viewAllItems

## MS Project
| Task Name | Duration | Predecessors | Assigned | Comments and clarification | Employees
I | Design library database and Mockup site |  |  |  |  | Tester A
1 | Plan and Design the Systems Database | 5 |  | DB Manager |  | Tester B
2 | Create the database based on the plan/design | 2 | 1 | DB Manager |  | Programmer A
3 | Test and review the Database | 2 | 2 | DB Manager, Project Manager |  | Programmer B
4 | Create website mockup pages | 5 |  | Programmer A |  | Programmer C
Sprint 1 - Add titles to database and search feature
II | Add new titles for the librarian |  |  |  |  | DB Manager
4 | Sprint planning, design and analysis | 1 |  | Project Manager, Programmer A,B,C Tester A,B,C, DB Manager
5 | Create a web form for registering new items | 1 | 3 | Programmer A |  | Project Manager
6 | Create a method that takes the values inside the form and store to database | 2 | 5 | Programmer B, DB Manager | Programmer B focuses on "add an item"
8 | Test the method if it stores new items succesfully | 1 | 7 | Tester A,B
9 | Fix bugs found | 2 | 8 | Programmer A
10 | Integrate the form and method inside the current build of system | 2 | 9 | Programmer B,C
III | Search an item feature of the system
4 | Sprint planning, design and analysis | 1 |  | Project Manager, Programmer A,B,C Tester A,B,C, DB Manager
16 | Create new class Search that contains an overloaded method that retrieves library items description and availability based on any provided search criteria | 3 | 3 | Programmer C
17 | Create database connectivity by writing an SQL string to connect and retrieve searched items from relevant tables in the database | 2 | 15 | Programmer C
18 | Test search method by typing various search queries | 1 | 16 | Programmer C
19 | Fix bugs found | 2 | 17 | Tester A,B
20 | Create web pages for entering and returning search items and link these pages to the main library website | 2 | 4 | Programmer A
21 | Test search feature in main library website | 2 | 19 | Programmer A
| Sprint review with entire team and client | 1 |  | Project Manager, Programmer A,B,C Tester A,B,C, DB Manager
Sprint 2 - Delete an item and reserve an item
IV | Deleting titles from the database
| Sprint planning, design and analysis | 1 |  | Project Manager, Programmer A,B,C Tester A,B,C, DB Manager
11 | Create method called delete_Items that shows existing items in database and option to delete selected items | 2 | 3 | Programmer B,C, DB Manager
12 | Connect method to the library database | 1 | 11 | Programmer B,C
13 | Test deleteItems method using test items | 1 | 12 | Tester A,B
14 | Debug delelteItems method | 2 | 13 | Programmer B,C
15 | Implement deleteItems method into main system and test | 2 | 14 | Programmer B,C
V | Reserve Function for user
38 | Create a reserve method to put a hold on the book that the student wants to borrow | 2 | 15 | Programmer B,C
39 | Connect method to the library database to record item and borrower information | 1 | 32 | Programmer B,C, DB Admin
40 | Test method with various users and items | 1 | 33 | Tester A,B
41 | fix bugs found | 2 | 34
42 | Integrate reserve method into software system after user searches for a book and test | 2 | 35 | Programmer B,C
| Sprint review with entire team and client | 1 |  | Project Manager, Programmer A,B,C Tester A,B,C, DB Manager
Sprint 3 - Check in/check out feature for users
VI | Check in feature for users
4 | Sprint planning, design and analysis | 1 |  | Project Manager, Programmer A,B,C Tester A,B,C, DB Manager
22 | Reuse the "checkout barcode reader" function, but integrates with check in feature | 2 | 21 | Programmer B
23 | Connect check in method to the database to update the database in accordance to the changes | 1 | 44 | Programmer B
24 | Test method by scanning items from library | 1 | 46 | Tester A,B
25 | Fix bugs found | 2 | 47 | Programmer B
26 | Integrate check in method with current running software and test feature again by scanning more items | 2 | 48 | Programmer B
VII | Checkout feature for the user |  |  |  | Done at the same timeline with feature VIIII
27 | Create checkout method that reads barcode numbers from library items | 2 |  | Programmer C | a CHECK-IN feature is also a must
28 | Connect checkout method to the database to record the scanned items with information on the library item and the borrower | 1 | 21 | Programmer C
29 | Test checkout method by scanning items from library | 1 | 22 | Tester A,C
30 | Fix bugs found | 2 | 23 | Programmer C
31 | Integrate checkout method with current running software and test feature again by scanning more items | 2 | 25 | Programmer C
| Sprint review with entire team and client | 1 |  | Project Manager, Programmer A,B,C Tester A,B,C, DB Manager
Sprint 4 - client registration and admin authorization for librarian
VIII | Client Registration System |  |  |  | Done before feature V
| Sprint planning, design and analysis | 1 |  | Project Manager, Programmer A,B,C Tester A,B,C, DB Manager
32 | Create a web form for new client registration | 1 | 3 | Programmer A
33 | Create a Register method that submits the web form to a database | 2 | 26 | Programmer C
34 | Connect the client reigstration method with the library database | 1 | 27 | Programmer C
35 | Test method by creating test user accounts | 1 | 28 | Tester A,B
36 | Fix bugs found | 2 | 29 | Programmer C,A
37 | Connect method to the created registration web form and test | 2 | 30 | Programmer C
| Sprint review with entire team and client | 1 |  | Project Manager, Programmer A,B,C Tester A,B,C, DB Manager
IX | Admin Authentication
50 | Create a form for admin registration(Librarian) | 1 |  | Programmer A
51 | Create a method that retrieves info from the form and pass it to database | 1 | 55 | Programmer B,C
52 | Create a form for admin (LOG IN PAGE) | 1 |  | Programmer A
53 | Create a method that retrieves info from the form and authenticate if user has enough credentials (username, pword) to log in | 1 | 57 | Programmer B,C
59 | Test the methods and look for log in exploits | 1 | 55 and 57 | Tester A,B
60 | Fix bugs and exploits found | 1 | 59 | Programmer B,C
61 | Integrate methods into the current system's build | 1 | 58 | Programmer B,C
| Sprint review with entire team and client | 1 |  | Project Manager, Programmer A,B,C Tester A,B,C, DB Manager
Sprint 5 - view reserved books feature for librarian
X | View reserve feature for librarian
| Sprint planning, design and analysis | 1 |  | Project Manager, Programmer A,B,C Tester A,B,C, DB Manager
43 | Team members researches for an efficient technology OR algorithm for a notifier | 1 |  | Programmer A,B,C
44 | Create a class for 'on hold' items that contains an overload method that retrieves and documents(viewable datasets) 'on hold' items, and notifies a librarian | 3 | 37 | Programmer B,C
45 | Connect the methods to the database | 1 | 38 | Programmer B,C
46 | Test the methods with user/librarian | 2 | 39 | Tester A,B
47 | Fix found bugs | 2 | 40 | Programmer B,C
48 | Integrate the methods and notifier in the website | 2 | 41 | Programmer B,C,A
49 | Test the feature to make sure the two technologies work together well | 1 | 42 | Programmer B,C,A
| Sprint review with entire team and client | 1 |  | Project Manager, Programmer A,B,C Tester A,B,C, DB Manager
| Sprint review with entire team and client | 1 |  | Project Manager, Programmer A,B,C Tester A,B,C, DB Manager
click this for chat:
https://hangouts.google.com/call/SZkNtwVR72tRKzRuF20LAAEE
angel come here
Up for deletion:
nyenyeneyneye
X | View titles(books, library stuff, etc..) that were requested by patrons |  |  |  | EXTRA FEATURE
49 | Create a form for requested items' information | 1 |  | Programmer B,C | do we really need it?
50 | Create a method that retrieves information from the form and takes them to database | 1 | 49 | Programmer B,C
51 | Create a view mode webpage for librarians to see requested titles | 1 | 50 | Programmer A
52 | Test the method | 1 | 50 | Tester A,B
53 | Fix bugs found | 1 | 51 | Programmer B,C
54 | Integrate method into the current system's build | 1 | 52 | Programmer B,C
List of things to do:
IMPORTANT NOTICE
1. Include planning stage
- he also said everybody has different style of project planning
Second
1.Review tasks
2. Review features for deletion
3. Number the predecessors
4. Add client review

## Copy of MS Project
| Task Name | Duration | Predecessors | Assigned | Comments and clarification | Employees
I | Design library database and Mockup site |  |  |  |  | Tester A
1 | Plan and Design the Systems Database | 5 |  | DB Manager | It's alright to have the DB man | Tester B
2 | Create the database based on the plan/design | 2 | 1 | DB Manager |  | Programmer A
3 | Test and review the Database | 2 | 2 | DB Manager, Project Manager |  | Programmer B
4 | Create website mockup pages | 5 |  | Programmer A |  | Programmer C
Sprint 1 - Add and delete titles from database
II | Add new titles for the librarian |  |  |  |  | DB Manager
4 | Sprint planning, design and analysis | 1 |  | Project Manager, Programmer A,B,C Tester A,B,C, DB Manager
5 | Create a web form for registering new items | 1 | 3 | Programmer A |  | Project Manager
6 | Create a method that takes the values inside the form and store to database | 2 | 5 | Programmer B, DB Manager | Programmer B focuses on "add an item"
8 | Test the method if it stores new items succesfully | 1 | 7 | Tester A,B
9 | Fix bugs found | 2 | 8 | Programmer A
10 | Integrate the form and method inside the current build of system | 2 | 9 | Programmer B,C
III | Deleting titles from the database
11 | Create method called delete_Items that shows existing items in database and option to delete selected items | 2 | 3 | Programmer B,C, DB Manager
12 | Connect method to the library database | 1 | 11 | Programmer B,C
13 | Test deleteItems method using test items | 1 | 12 | Tester A,B
14 | Debug delelteItems method | 2 | 13 | Programmer B,C
15 | Implement deleteItems method into main system and test | 2 | 14 | Programmer B,C
| Sprint review with entire team and client | 1 |  | Project Manager, Programmer A,B,C Tester A,B,C, DB Manager
Sprint 2 - Search for and item and reserve an item
IV | Search an item feature of the system
4 | Sprint planning, design and analysis | 1 |  | Project Manager, Programmer A,B,C Tester A,B,C, DB Manager
16 | Create new class Search that contains an overloaded method that retrieves library items description and availability based on any provided search criteria | 3 | 3 | Programmer C
17 | Create database connectivity by writing an SQL string to connect and retrieve searched items from relevant tables in the database | 2 | 15 | Programmer C
18 | Test search method by typing various search queries | 1 | 16 | Programmer C
19 | Fix bugs found | 2 | 17 | Tester A,B
20 | Create web pages for entering and returning search items and link these pages to the main library website | 2 | 4 | Programmer A
21 | Test search feature in main library website | 2 | 19 | Programmer A
VII | Reserve Function for user
38 | Create a reserve method to put a hold on the book that the student wants to borrow | 2 | 15 | Programmer B,C
39 | Connect method to the library database to record item and borrower information | 1 | 32 | Programmer B,C, DB Admin
40 | Test method with various users and items | 1 | 33 | Tester A,B
41 | fix bugs found | 2 | 34
42 | Integrate reserve method into software system after user searches for a book and test | 2 | 35 | Programmer B,C
| Sprint review with entire team and client | 1 |  | Project Manager, Programmer A,B,C Tester A,B,C, DB Manager
Sprint 3 - Check in/check out feature for users
VIIII | Check in feature for users
4 | Sprint planning, design and analysis | 1 |  | Project Manager, Programmer A,B,C Tester A,B,C, DB Manager
22 | Reuse the "checkout barcode reader" function, but integrates with check in feature | 2 | 21 | Programmer B
23 | Connect check in method to the database to update the database in accordance to the changes | 1 | 44 | Programmer B
24 | Test method by scanning items from library | 1 | 46 | Tester A,B
25 | Fix bugs found | 2 | 47 | Programmer B
26 | Integrate check in method with current running software and test feature again by scanning more items | 2 | 48 | Programmer B
V | Checkout feature for the user |  |  |  | Done at the same timeline with feature VIIII
27 | Create checkout method that reads barcode numbers from library items | 2 |  | Programmer B | a CHECK-IN feature is also a must
28 | Connect checkout method to the database to record the scanned items with information on the library item and the borrower | 1 | 21 | Programmer B
29 | Test checkout method by scanning items from library | 1 | 22 | Tester A,B
30 | Fix bugs found | 2 | 23 | Programmer B
31 | Integrate checkout method with current running software and test feature again by scanning more items | 2 | 25 | Programmer B
| Sprint review with entire team and client | 1 |  | Project Manager, Programmer A,B,C Tester A,B,C, DB Manager
Sprint 4 - client registration and admin authorization for librarian
VI | Client Registration System |  |  |  | Done before feature V
| Sprint planning, design and analysis | 1 |  | Project Manager, Programmer A,B,C Tester A,B,C, DB Manager
32 | Create a web form for new client registration | 1 | 3 | Programmer A
33 | Create a Register method that submits the web form to a database | 2 | 26 | Programmer C
34 | Connect the client reigstration method with the library database | 1 | 27 | Programmer C
35 | Test method by creating test user accounts | 1 | 28 | Tester A,B
36 | Fix bugs found | 2 | 29 | Programmer C,A
37 | Connect method to the created registration web form and test | 2 | 30 | Programmer C
| Sprint review with entire team and client | 1 |  | Project Manager, Programmer A,B,C Tester A,B,C, DB Manager
IX | Admin Authentication
50 | Create a form for admin registration(Librarian) | 1 |  | Programmer A
51 | Create a method that retrieves info from the form and pass it to database | 1 | 55 | Programmer B,C
52 | Create a form for admin (LOG IN PAGE) | 1 |  | Programmer A
53 | Create a method that retrieves info from the form and authenticate if user has enough credentials (username, pword) to log in | 1 | 57 | Programmer B,C
59 | Test the methods and look for log in exploits | 1 | 55 and 57 | Tester A,B
60 | Fix bugs and exploits found | 1 | 59 | Programmer B,C
61 | Integrate methods into the current system's build | 1 | 58 | Programmer B,C
| Sprint review with entire team and client | 1 |  | Project Manager, Programmer A,B,C Tester A,B,C, DB Manager
Sprint 5 - view reserved books feature for librarian
VIII | View reserve feature for librarian
| Sprint planning, design and analysis | 1 |  | Project Manager, Programmer A,B,C Tester A,B,C, DB Manager
43 | Team members researches for an efficient technology OR algorithm for a notifier | 1 |  | Programmer A,B,C
44 | Create a class for 'on hold' items that contains an overload method that retrieves and documents(viewable datasets) 'on hold' items, and notifies a librarian | 3 | 37 | Programmer B,C
45 | Connect the methods to the database | 1 | 38 | Programmer B,C
46 | Test the methods with user/librarian | 2 | 39 | Tester A,B
47 | Fix found bugs | 2 | 40 | Programmer B,C
48 | Integrate the methods and notifier in the website | 2 | 41 | Programmer B,C,A
49 | Test the feature to make sure the two technologies work together well | 1 | 42 | Programmer B,C,A
| Sprint review with entire team and client | 1 |  | Project Manager, Programmer A,B,C Tester A,B,C, DB Manager
| Sprint review with entire team and client | 1 |  | Project Manager, Programmer A,B,C Tester A,B,C, DB Manager
click this for chat:
https://hangouts.google.com/call/SZkNtwVR72tRKzRuF20LAAEE
angel come here
Up for deletion:
nyenyeneyneye
X | View titles(books, library stuff, etc..) that were requested by patrons |  |  |  | EXTRA FEATURE
49 | Create a form for requested items' information | 1 |  | Programmer B,C | do we really need it?
50 | Create a method that retrieves information from the form and takes them to database | 1 | 49 | Programmer B,C
51 | Create a view mode webpage for librarians to see requested titles | 1 | 50 | Programmer A
52 | Test the method | 1 | 50 | Tester A,B
53 | Fix bugs found | 1 | 51 | Programmer B,C
54 | Integrate method into the current system's build | 1 | 52 | Programmer B,C
List of things to do:
IMPORTANT NOTICE
1. Include planning stage
- he also said everybody has different style of project planning
Second
1.Review tasks
2. Review features for deletion
3. Number the predecessors
4. Add client review